## Roadmap_12M
12-Month Digital Transformation Roadmap
Teal = process/data foundations (committed); amber = ERP phase (conditional on Gate 1); grey = enabling; red = decision gate. Months from approval date.
# | Workstream | Activity | Owner | Start | End | Deliverable / exit criterion | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
1 | 0 Mobilise | Steering committee, PMO, benefit owners, baselines | CEO / PMO | 1 | 2 | Charter, RACI, KPI baseline pack | bar: M1 to M2
2 | 0 Mobilise | Time-and-motion study (PO, search/recount, report prep) | PMO / Finance | 1 | 2 | Validated hours; replaces management estimates | bar: M1 to M2
3 | 1 Data | Item master clean-up: dedupe, naming standard, unit of measure, golden record | IT Manager | 1 | 4 | Single code per item; duplicate rate < 2% | bar: M1 to M4
4 | 1 Data | Supplier and customer master clean-up (126 / 74) | Procurement / Sales | 2 | 4 | Verified masters with owners | bar: M2 to M4
5 | 2 Process | ABC-XYZ classification; min/max and reorder policy; slow-mover list | Warehouse Mgr / Finance | 2 | 4 | Policy approved; slow-movers actioned | bar: M2 to M4
6 | 2 Process | Cycle-count programme; bin/location rules; adjustment approvals with cause codes | Warehouse Mgr | 2 | 6 | Accuracy >= 90% both plants (Gate 1 evidence by M3 trend) | bar: M2 to M6
7 | 2 Process | Procurement SOP: one requisition form, duplicate check, approval matrix, emergency order code | Procurement Mgr | 2 | 5 | Duplicate POs < 1%; emergency orders <= 8% | bar: M2 to M5
8 | 2 Process | S&OP-lite weekly, 48-72h schedule freeze, change log, one shared schedule | Production Mgr / COO | 2 | 6 | Schedule adherence >= 86% | bar: M2 to M6
9 | 2 Process | Reporting rationalisation: 40 reports to ~15 KPI pack; automate refresh | Finance / IT | 3 | 6 | Report hours <= 190/month | bar: M3 to M6
10 | 3 Quality | Rework root-cause programme: calibration, SPC, supplier quality, operator skills (outside ERP benefit case) | Production Mgr / QA | 2 | 8 | Rework <= 4.0% (not credited to ERP) | bar: M2 to M8
11 | 4 Cyber | MFA, access reviews, 3-2-1 immutable backup, incident response plan, tabletop | IT Manager | 1 | 4 | Controls evidenced; restore test passed | bar: M1 to M4
12 | 5 ERP selection | RFP, demos, references, security assurance; firm fixed-price quotes | PMO / IT / CFO | 1 | 3 | Shortlist scored; quotes valid 90 days | bar: M1 to M3
13 | GATE 1 | ERP commitment decision (month 4): commercial terms, readiness evidence, refreshed model | Steering Committee | 4 | 4 | Go only if all Gate 1 criteria met (see Gates_KPIs) | bar: M4
14 | 6 ERP build | Design workshops, configuration (finance, procurement, inventory, sales orders, basic planning) | Vendor / Process owners | 4 | 8 | Signed-off blueprint, configured system | bar: M4 to M8
15 | 6 ERP build | Integrations, scanning hardware, labels, role-based access, SSO/MFA | IT / Vendor | 6 | 9 | Interfaces tested; devices in both plants | bar: M6 to M9
16 | 6 ERP build | Data migration: 3 trial loads and reconciliation | IT / Finance | 6 | 9 | >= 99.5% reconciliation; ledger tie-out | bar: M6 to M9
17 | 7 People | Change impact assessment, super-users, role-based training (max 4h/week/employee), comms | HR / PMO | 5 | 11 | >= 90% trained before cutover; proficiency check | bar: M5 to M11
18 | 8 Cutover | UAT, GATE 2 go/no-go (month 10) | Steering Committee | 9 | 10 | UAT pass, trial reconciliation, rollback plan | bar: M9 to M10
19 | 8 Cutover | Wave 1: finance, procurement, sales orders | PMO | 10 | 10 | Parallel run 4 weeks | bar: M10
20 | 8 Cutover | Wave 2: Plant B inventory and planning | COO / Plant B | 11 | 11 | Stock count tie-out > 98% | bar: M11
21 | 8 Cutover | Wave 3: Plant A inventory and planning | COO / Plant A | 12 | 12 | Stock count tie-out > 98%; no OTD drop > 3pp | bar: M12
22 | 9 Benefits | Hypercare; weekly KPI review; benefit realisation report; Gate 3 (analytics option) in month 15+ | CFO / PMO | 12 | 12 | Benefits tracked vs model | bar: M12

## Gates_KPIs
Stage gates and KPI tracker
Gate | Month | Criterion | Threshold | Evidence owner | Status
Gate 1: ERP commitment | 4 | Firm vendor quote: implementation components | <= RM 700k fixed price, 15% holdback | CFO / PMO | Open
Gate 1: ERP commitment | 4 | Licence & support | <= RM 180k p.a.; <= 3% annual uplift for 3 years | CFO | Open
Gate 1: ERP commitment | 4 | Refreshed model (CFO-signed) at firm quotes: base case | NPV >= 0 at 12%, IRR >= 15%, payback <= 36 months, total commitment <= RM 1.2m | CFO | Open
Gate 1: ERP commitment | 4 | Conservative-case check | NPV not worse than -RM 0.5m; cap on commitment holds under 25% overrun | CFO | Open
Gate 1: ERP commitment | 4 | Master data readiness | Duplicate item codes < 2%; A/B-class items 100% cleansed | IT Manager | Open
Gate 1: ERP commitment | 4 | Process evidence | Stock accuracy >= 90% in cycle-counted ABC zones; emergency orders trending <= 9% | Warehouse / Procurement | Open
Gate 1: ERP commitment | 4 | Validated baselines | Time study complete; benefit owners named for each line | PMO | Open
Gate 1: ERP commitment | 4 | Capacity | Backfill plan funded; ERP partner PMO contracted; ERP admin identified | CEO / HR | Open
Gate 2: Cutover go/no-go | 10 | Data migration | >= 99.5% reconciliation in last trial; ledger ties to the sen | IT / Finance | Open
Gate 2: Cutover go/no-go | 10 | UAT and training | No open severity-1/2 defects; >= 90% staff trained and proficiency-checked | PMO / HR | Open
Gate 2: Cutover go/no-go | 10 | Operational readiness | Rollback plan tested; customer comms sent; peak-order calendar respected | COO | Open
Gate 3: Analytics option | 15 | Data maturity and ERP benefits | 12 months clean data; inventory days <= 70; benefit tracking >= 90% of model | CFO / COO | Open
KPI tracker
KPI | Baseline 2026 | Month 6 target | Month 12 target | Month 24 target | Owner | Frequency | Source
Inventory days | 79 | 76 | 74 | 68 | CFO | Monthly | Inventory valuation / COGS
Inventory accuracy (%) | 86% | 90% | 92% | 94% | Warehouse Mgr | Weekly (cycle counts) | Count results
Emergency orders (% of POs) | 11% | 8% | 7% | 5% | Procurement Mgr | Monthly | PO log, cause codes
Duplicate POs (%) | 2.8% | 1% | 0.5% | 0.3% | Procurement Mgr | Monthly | PO log
PO processing time (min) | 42 | 37 | 32 | 27 | Procurement Mgr | Quarterly sample | Time study
Monthly reporting hours | 260 | 190 | 150 | 130 | Finance Mgr | Monthly | Timesheet sample
On-time delivery (%) | 87% | 88% | 90% | 92% | COO | Weekly | Delivery log
Schedule adherence (%) | 82% | 86% | 88% | 89% | Production Mgr | Weekly | Schedule vs actual
Overtime (RM k, annualised) | 560 | 500 | 450 | 400 | Production Mgr | Monthly | Payroll
Inventory write-offs (RM k, annualised) | 312 | 270 | 230 | 200 | CFO | Quarterly | GL
Rework rate (%) | 4.6% | 4.3% | 4% | 3.8% | QA | Weekly | QA log (not credited to ERP)
Stockout incidents / month | 45 | 40 | 32 | 25 | Warehouse Mgr | Weekly | Stockout log
Training completion (%) | 0 | 30% | 90% | 1 | HR | Weekly | LMS / attendance
Active user adoption (%) | 0 | 0 | 85% | 95% | PMO | Weekly | System logs

## Governance_RACI
Governance and accountability (RACI)
R = Responsible, A = Accountable, C = Consulted, I = Informed
Decision / deliverable | CEO | CFO | COO | Prod Mgr | Procure Mgr | Warehouse Mgr | IT Mgr | HR Mgr | Vendor/PMO
Programme charter, gates, scope freeze | A | R | R | C | C | C | C | C | R
Master data standard and ownership | I | C | C | C | R | R | A | I | C
Inventory policy (ABC, safety stock, counts) | I | C | A | C | C | R | I | I | C
Procurement SOP and approvals | I | C | C | C | A | C | I | I | R
S&OP-lite and schedule freeze | I | C | A | R | C | C | I | I | C
Vendor selection and contract | C | A | C | C | R | C | R | I | R
Benefit baseline and tracking | I | A | R | R | R | R | C | I | C
ERP configuration and testing | I | C | C | R | R | R | A | I | R
Data migration sign-off | I | R | C | C | C | C | A | I | R
Training and change plan | I | I | C | C | C | C | C | A | R
Cyber controls and vendor assurance | I | C | I | I | I | I | A | I | R
Cutover go/no-go | C | R | A | R | C | R | R | C | R
Steering committee: CEO (chair), CFO, COO, IT Manager, HR Manager; meets bi-weekly in build, monthly otherwise. Decision rights: gates, scope, budget >5% variance.

## Training_Change
Training and change management plan
Training windows must not remove staff from production for extended periods (max 4 hours/week/employee).
Audience | Headcount (est.) | Hours per person | Total hours | Format | Timing | Release rule
Super-users (2 per area) | 16 | 40 | 640 | Vendor workshops + sandbox | M5-M9 | Backfilled; 20% time
Procurement | 8 | 16 | 128 | Role-based, hands-on | M9-M10 | Two cohorts; never both on same shift
Finance and admin | 10 | 20 | 200 | Role-based + reconciliation drills | M9-M10 | Avoid month-end
Planners and production supervisors | 24 | 12 | 288 | Scenario-based | M9-M11 | Outside schedule-freeze window
Warehouse (both plants) | 21 | 10 | 210 | Scanner practice on the floor | M10-M11 | Shift-based; 30-min blocks
Machine operators (read-only / shop-floor screens) | 70 | 3 | 210 | Toolbox talks | M11-M12 | Start of shift
IT team (3) | 3 | 60 | 180 | Admin certification | M6-M10 | Vendor-paid where possible
Management dashboards | 12 | 4 | 48 | KPI walk-through | M11 | Within meetings
Total training hours |  |  | 1904
Average hours per employee (185) |  |  | 10.2919
Note: headcounts are estimates for planning; replace with HR roster. Operators outside the 185 split are not double counted if the roster differs.