## Slide 1
Digital transformation and ERP investment decision
Meridian Precision Components Sdn. Bhd. | Investment Committee presentation
Independent assessment: root causes, cost of inefficiency, options, five-year financial case (2027-2031) and 12-month roadmap. Fictional case; synthetic data.
Notes: Opening: the board asked six questions. This deck answers them in order and ends with a decision request.

## Slide 2
Fix the foundations now; make the ERP earn its place at a gate in month 4
+RM 0.36m
Option A: process, data and controls. RM 0.27m loaded; payback 11 months; passes every board test
-RM 0.09m
Option B: cloud ERP today. RM 1.19m loaded; IRR 8.7% vs 12% hurdle; payback 40 months
-RM 1.26m
Option C: ERP plus analytics. RM 1.93m loaded breaches the RM 1.5m cap; go-live month 14
Recommendation: approve Option A now (RM 0.27m, ceiling RM 0.30m); reject C; pre-authorise an ERP envelope of up to RM 1.2m released only if Gate 1 criteria are met. NPV at 12%, five-year, base case, including one-time inventory cash release.
Notes: NPV figures include one-time working-capital release. Excluding it, A is about break-even (-RM 0.02m) and B is -RM 1.07m: the economics rest on inventory cash, not recurring savings.

## Slide 3
Revenue grew 22% but EBITDA did not move: leakage grew faster than the business
Chart: Index, 2024 = 100
| 2024 | 2025 | 2026
Revenue | 100 | 111 | 122
Inventory | 100 | 123 | 156
Overtime | 100 | 128 | 175
Write-offs | 100 | 143 | 215
Emergency buying | 100 | 153 | 233
5.40 > 5.35
EBITDA RM m, 2024 vs 2026 (margin 13.6% to 11.0%)
-2.2 pp
Gross margin 25.9% to 23.7% = RM 1.08m gap
86%
Stock accuracy (94% in 2024); inventory days 64 to 79

## Slide 4
Neither explanation is complete: operations explain about two-thirds of the margin gap
Chart: Excess over 2024 intensity, RM thousand (total gap RM 1,077k)
| Emergency buying | Write-offs | Overtime | Rework (estimate) | Residual: material, mix, price (unverified)
RM thousand | 200 | 135 | 169 | 208 | 365
Operations: 66% of the gap (47% without the rework estimate).
CFO: material costs may explain the residual 34-53%, but no commodity or price-variance data was supplied to test it.
Not an ERP promise: only part of the operational share is addressable by any system.

## Slide 5
The cash cost is RM 0.71m a year; the larger prize is a one-time RM 1.42m inventory release
Chart: RM thousand per year
| Emergency | Write-offs | Overtime | Rework (est.)
2026 gross cost | 420 | 312 | 560 | 683
Avoidable excess | 200 | 135 | 169 | 208
RM 1.42m
Inventory 79 to 65 days = 14 days x RM 102k COGS/day. One-time cash, not a saving
RM 0.33m
Staff time (PO, reporting, search) is capacity, not payroll: 8 buyers retained, so cash value is only the 35% monetised share
Notes: Operations Director estimated RM 600k. Our bottom-up: search labour 121k + emergency excess 200k + overtime excess 169k + write-off excess 135k = RM 625k, so the order of magnitude holds, but 121k is capacity not cash and rework (208k) sits outside his scope. Interest on released stock is excluded to avoid double counting with the 12% discount rate.

## Slide 6
Most problems need process and data fixes first; only some need technology
Process-led | Process + technology | Technology-led
Excess safety stock (policy, ABC-XYZ) Rework 4.6% (calibration, material, skills) Material price pass-through Schedule freeze and change control | Duplicate item codes (master data) Stock accuracy 86% Duplicate and emergency POs On-time delivery 87% Overtime +75% | Cross-plant stock visibility Automated three-way match Lot traceability 260 report-hours a month Order-to-plan data flow
Sequencing follows from this: clean data and install controls first. An ERP on dirty master data would automate the confusion.

## Slide 7
Only Option A clears every board criterion at today's estimates
Route | Loaded initial | NPV @12% | NPV excl. WC | IRR | Payback | Board test
A: Process improvement | RM 0.27m | +RM 0.36m | -RM 0.02m | 76.6% | 11 mo | PASS
B: Cloud ERP | RM 1.19m | -RM 0.09m | -RM 1.07m | 8.7% | 40 mo | FAIL
C: ERP + analytics | RM 1.93m | -RM 1.26m | -RM 2.43m | -17.6% | none | FAIL
P: Phased: A, then gated ERP | RM 1.32m | -RM 0.11m | -RM 1.10m | 8.3% | 41 mo | FAIL
Criteria: NPV > 0 at 12%, IRR > 12%, ROI >= 20%, payback <= 36 months, initial investment <= RM 1.5m. Initial includes vendor estimate, overrun allowance, internal backfill, scanners and cyber set-up. A passes mainly through inventory cash release; its recurring savings roughly cover recurring cost.

## Slide 8
Downside risk is asymmetric: ERP options lose value fast, Option A loses little
Chart: NPV incl. WC release, RM m
| Base | Conservative | Downside
A Process | 0.36 | 0.08 | -0.17
B Cloud ERP | -0.09 | -0.92 | -1.65
C ERP+analytics | -1.26 | -2.33 | -3.33
P Phased | -0.11 | -0.95 | -1.7
Conservative: +25% cost, 3-month delay, 80% of benefits, slower adoption.
Downside: +40% cost, 6-month delay, 60% of benefits, no monetised time.
Cap check: Option P reaches RM 1.54m in the downside, so the Gate 1 commitment ceiling is RM 1.2m.

## Slide 9
Taking management's KPI claims at face value inflates the ERP case by RM 1.06m
Chart: Option B NPV, RM m
| Management claims (unadjusted) | Credited (base)
Option B NPV, RM m | 0.96 | -0.09
Four integrity rules applied
Time saved is not payroll saved: 35% of hours monetised (claims: 100%).
Rework gets 12% credit only; ERP does not fix calibration or skills.
Inventory cash is counted once, as one-time WC; interest on it is excluded.
Each cost sits in one line only (emergency, write-off, overtime, search).

## Slide 10
The ERP is a near break-even; four things would make it clearly worth buying
104%
Benefit realisation needed to break even (credited = 100%)
RM 185k
Licence ceiling (quote: RM 210k)
RM 738k
Implementation ceiling (quote: RM 820k)
67.0 days
Inventory days ERP must deliver (credited 68)
Gate 1 commercial test: implementation RM 700k fixed price + licence RM 180k, 3% annual cap gives NPV +RM 0.16m, IRR 17.8%, payback 27 months. If the ERP also reaches 66 days: NPV +RM 0.34m.
Incremental ERP over Option A is -RM 0.47m NPV at today's quotes: ERP must be bought on better terms and proven benefits, or not at all.

## Slide 11
Waiting a year costs little for the ERP but real money for the basic fixes
RM 51k
NPV lost by delaying Option A one year (plus RM 71-178k extra leakage if erosion runs 10-25%)
RM 43k
NPV lost by delaying Option B one year: small because the case is marginal
RM 3.6m
Five-year leakage if nothing changes (RM 0.71m a year, flat); worse if the 2024-26 trend continues
Implication: do not rush the ERP, do not delay the controls. The three leakage lines alone rose about RM 0.4m between 2025 and 2026.
Notes: Delay cost = base NPV minus delayed NPV discounted one year with 5% cost inflation; leakage erosion shown as extra exposure rather than benefit.

## Slide 12
12-month roadmap: foundations first, ERP phase conditional on Gate 1
M1
M2
M3
M4
M5
M6
M7
M8
M9
M10
M11
M12
Mobilise, baselines, time study
Master data clean-up
Inventory, procurement, S&OP controls
Cyber baseline
ERP RFP and firm quotes
GATE 1 (month 4)
ERP design, build, migration trials
Training, UAT, GATE 2 (month 10)
Cutover: Fin/Proc, Plant B, Plant A
Teal = committed foundations. Amber = ERP phase, released only if Gate 1 passes. Grey = enabling. Red = decision gate.

## Slide 13
Protecting production and people: wave cutover, capped training, honest readiness data
Production continuity
Plant B first (worst accuracy 83%, lower customer risk), Plant A last
Three trial loads; go only at >= 99.5% reconciliation
Four-week parallel run; weekend cutover; rollback plan
Training capped at 4 hours per person per week; 16 super-users backfilled
Cyber: MFA, immutable backups, vendor ISO 27001 / SOC 2 evidence
Chart: 
| Systems create unnecessary work | Integrated systems would help | Worried about new software | Fear automation cuts jobs | Confident in digital skills
Agreement % | 78 | 72 | 61 | 44 | 39
Survey: 120 of 185 staff, method unclear. Worst-case floor for the 78% result is 51% of all staff. Re-run a stratified pulse survey by function and shift before designing training.

## Slide 14
Top risks are data, benefits and adoption; each has a named owner and trigger
Risk | Mitigation | Owner
Master data duplicates migrate into ERP | Clean-up before migration; <2% duplicates at Gate 1 | IT Mgr
Benefits do not materialise | Time study, benefit owners, Gate 1 refresh of model | CFO
Cost overrun beyond estimates | Fixed price, 15% holdback, RM 1.2m ceiling | CFO
Cutover disrupts production | Plant-by-plant waves, parallel run, rollback | COO
Employees resist or cannot adopt | No-redundancy statement, super-users, capped training | HR Mgr
Stockouts rise as stock is cut | ABC-XYZ cuts, protect A-items, stop-rule at 45/month | Whse Mgr
Full register: 20 risks, 8 High inherent, average score falling from 13.1 to 6.6 after mitigation (07_Risk_Register.xlsx).

## Slide 15
Decisions requested today
1. Approve Phase 1 (Option A+): RM 0.27m base, ceiling RM 0.30m
2. Pre-authorise an ERP envelope of up to RM 1.2m, released by the steering committee only if every Gate 1 criterion is met in month 4
3. Reject Option C; revisit analytics at Gate 3 (month 15+) on 12 months of clean data
4. Fund an ERP partner PMO, key-user backfill and one ERP administrator
5. Commission the time study and vendor RFP in the first 30 days