## Risk_Register
Programme Risk Register
Score = Likelihood x Impact (1-5). Rating: >=15 High, 8-14 Medium, <8 Low. Edit blue cells; scores and ratings recalculate.
ID | Category | Risk | Cause / trigger | L | I | Score | Rating | Mitigation | Early-warning indicator | Owner | Residual L | Residual I | Residual score | Status
R01 | Data | Master data duplicates migrate into ERP (same item under several codes) | 2,850 SKUs, no governance; IT Manager warning | 5 | 5 | 25 | High | Phase 1 data clean-up before any migration; golden-record rules; 3 trial loads with >=99.5% reconciliation as go/no-go | Duplicate rate after clean-up > 2% | IT Manager | 2 | 4 | 8 | Open
R02 | Financial | Vendor costs exceed preliminary estimates | Estimates are not quotations | 4 | 4 | 16 | High | Firm fixed-price quotes at Gate 1; 15% holdback; change-control board; contingency 15% held by CFO | Change requests > 5% of scope | CFO | 3 | 3 | 9 | Open
R03 | Financial | Benefits do not materialise (base case is break-even for ERP) | Credited benefits unverified; time-and-motion not done | 4 | 5 | 20 | High | Baseline time study; named benefit owners; quarterly benefit review; Gate 1 refresh of model with real data | Inventory days not <= 76 by M6 | CFO / COO | 3 | 4 | 12 | Open
R04 | Financial | Licence price escalation after year 1 | SaaS renewal uplift | 3 | 3 | 9 | Medium | Contract cap <= 3% p.a. for 3 years; multi-year price lock | Renewal notice > cap | CFO | 2 | 2 | 4 | Open
R05 | Operational | Production disruption at cutover | Plants run on live inventory; transaction freeze | 3 | 5 | 15 | High | Plant B first; weekend cutover; 4-week parallel run; rollback plan; freeze windows outside peak orders | Trial-load variance > 0.5% | COO | 2 | 4 | 8 | Open
R06 | Operational | Stockouts rise when inventory targets are tightened | Warehouse manager concern; safety stock cuts | 4 | 4 | 16 | High | Reduce by ABC-XYZ class; protect A-items; slow-mover liquidation first; weekly stockout review with stop-rule | Stockouts > 45/month for 2 weeks | Warehouse Mgr | 2 | 3 | 6 | Open
R07 | Operational | Inventory counts disrupt production | Cycle-count programme resourcing | 3 | 3 | 9 | Medium | Cycle counts in low-activity windows; dedicated count team of 2; ABC frequencies | Count overruns > 2 hrs/day | Warehouse Mgr | 2 | 2 | 4 | Open
R08 | People | Employee resistance and low adoption | 61% worried about new software; 44% fear job loss | 4 | 4 | 16 | High | No-redundancy commitment attributable to ERP; super-users per area; WIIFM comms; incentives tied to data accuracy | Login/usage < 80% by week 4 | HR Manager | 3 | 3 | 9 | Open
R09 | People | Survey results over-state readiness | Unclear sampling; 120 of 185 | 3 | 3 | 9 | Medium | Stratified pulse survey by function/shift before training design; focus groups with operators | Low turnout from shift workers | HR Manager | 2 | 2 | 4 | Open
R10 | People | Key-person dependence (3 IT staff, few process owners) | Small team; SMEs rely on individuals | 4 | 4 | 16 | High | Backfill for key users; retained ERP partner PMO; documented processes; cross-training | Overtime > 15% for IT staff | IT Manager | 3 | 3 | 9 | Open
R11 | Technical | Integration with standalone accounting software fails or is delayed | Legacy finance system | 3 | 4 | 12 | Medium | Prefer ERP finance module; migrate GL balances + open items; reconciliation controls | Interface defect backlog > 20 | IT Manager | 2 | 3 | 6 | Open
R12 | Technical | Data loss or corruption in migration | Complex multi-source spreadsheets | 2 | 5 | 10 | Medium | Immutable backups pre-load; reconciliation scripts; archive of legacy files; audit trail | Failed reconciliation in trial load | IT Manager | 1 | 5 | 5 | Open
R13 | Cyber | Ransomware / credential compromise during transition | Basic endpoint protection only today | 3 | 5 | 15 | High | MFA everywhere; offsite immutable backup (3-2-1); incident response plan and tabletop; privileged-access review | Phishing click-rate > 8% | IT Manager | 2 | 4 | 8 | Open
R14 | Cyber | Vendor security breach or inadequate assurance | SaaS dependency | 2 | 5 | 10 | Medium | ISO 27001/SOC 2 evidence; data-processing agreement; breach notification SLA; exit clause | Audit findings open > 30 days | IT Manager | 1 | 5 | 5 | Open
R15 | Scope | Scope creep toward advanced planning / analytics (Option C features) | Production Manager preference for APS | 4 | 3 | 12 | Medium | Freeze scope at Gate 1; park APS/forecasting as Phase 3 gated on 12 months of clean data | Change requests citing APS | Steering Committee | 2 | 3 | 6 | Open
R16 | Governance | Decision delay or divided management (CFO sceptical, COO supportive) | Competing priorities | 3 | 4 | 12 | Medium | Steering committee with decision rights; Gate criteria agreed upfront; monthly benefits report | Gate decision slips > 4 weeks | CEO | 2 | 3 | 6 | Open
R17 | Quality | Rework not reduced (wrongly attributed to ERP) | Calibration, material, skills are separate causes | 4 | 3 | 12 | Medium | Separate engineering root-cause programme; SPC; calibration schedule; supplier quality; excluded from ERP benefits | Rework rate > 4.5% at M6 | Production Manager | 3 | 3 | 9 | Open
R18 | Compliance | Statutory changes (e-invoicing, SST, PDPA) not covered | Regulatory phase-in | 2 | 3 | 6 | Low | Vendor compliance commitment; CFO check at design; PDPA data map | Compliance gap at UAT | CFO | 1 | 3 | 3 | Open
R19 | Commercial | Customer service dips during transition (OTD) | Shortages, order-entry errors | 3 | 4 | 12 | Medium | Customer comms for top accounts; daily OTD watch; temporary expedite budget | OTD < 85% for 2 weeks | COO | 2 | 3 | 6 | Open
R20 | Supplier | Supplier lead-time shocks mask improvement | External market | 3 | 3 | 9 | Medium | Safety stock for single-source A-items; supplier scorecards; dual-source critical materials | Lead time > 22 days | Procurement Mgr | 2 | 2 | 4 | Open

## Heat_Map
Inherent risk heat map (count of risks by Likelihood x Impact)
L \ I | 1 | 2 | 3 | 4 | 5
5 | 0 | 0 | 0 | 0 | 1
4 | 0 | 0 | 2 | 4 | 1
3 | 0 | 0 | 4 | 3 | 2
2 | 0 | 0 | 1 | 0 | 2
1 | 0 | 0 | 0 | 0 | 0
Summary
High (inherent) | 8
Medium (inherent) | 11
Low (inherent) | 1
Average inherent score | 13.05
Average residual score | 6.55