## Weighted_Matrix
Technology Options and Investment Evaluation Matrix
Scores 1-5 (5 = best; for risk criteria 5 = lowest risk). Blue cells are editable judgments; totals are formulas.
Criterion | Weight | A: Process improvement | B: Cloud ERP | C: ERP + analytics | P: Phased route (A now, gated ERP) | Rationale
Financial return (NPV, IRR, payback, board hurdles) | 25% | 5 | 2 | 1 | 3 | Base NPV: A +RM 0.36m; B -0.09m; C -1.26m; P -0.11m (before commercial terms). See model.
Fit to root causes (data, controls, integration) | 15% | 3 | 4 | 3 | 5 | Root causes are master data, control discipline and fragmentation; P addresses all three in the right order.
Implementation risk | 15% | 5 | 3 | 1 | 4 | C: 14-month go-live incl. selection, advanced planning on immature data. P de-risks migration by cleaning data first.
Production continuity | 10% | 5 | 3 | 2 | 4 | Phased plant cutover (Plant B first) and weekend loads in P; C touches scheduling logic at both plants simultaneously.
Capacity of 3-person IT team | 10% | 4 | 3 | 1 | 3 | C needs ~2 extra FTE equivalent; backfill and retained partner required for B/P.
Scalability and growth readiness | 10% | 1 | 4 | 5 | 4 | Spreadsheet-based A hits a ceiling around 2-plant, 2,850-SKU complexity as volume grows.
Cybersecurity and data governance | 5% | 2 | 4 | 4 | 4 | Reputable cloud ERP gives role-based access, audit trail; A leaves data in spreadsheets.
Budget and board constraints (<= RM 1.5m, <= 12 months) | 10% | 5 | 4 | 1 | 4 | C breaches cap on a loaded basis (RM 1.93m) and horizon (month 14).
Weighted score (out of 5) | 100% | 4.05 | 3.15 | 1.95 | 3.8
Rank |  | 1 | 3 | 4 | 2
Reading: A scores highest because it is cheap and low-risk, but it scores 1 on scalability. The recommendation is therefore A now (committed) with a pre-defined, gated option to proceed to the ERP core (P) - not A forever, and not B or C today.

## Constraints_Check
Feasibility against client constraints
Status: PASS / CONDITIONAL / FAIL
Constraint | A | B | C | P | Evidence / condition
Both plants operational throughout | PASS | CONDITIONAL | FAIL | CONDITIONAL | B/P: wave cutover, Plant B first, parallel run 4 weeks, weekend loads. C: advanced scheduling change in both plants at once.
Historical data preserved | PASS | CONDITIONAL | CONDITIONAL | CONDITIONAL | Migrate 3 years of transactions + all open documents; archive older data read-only; reconcile to ledger.
No extended training removal from production | PASS | CONDITIONAL | FAIL | CONDITIONAL | Max 4 hrs/week/employee, shift-based sessions, super-users; C needs ~40% more training hours.
Cybersecurity controls (access, backup, IR, vendor assurance) | CONDITIONAL | PASS | PASS | PASS | A needs MFA/backup upgrades regardless. B/C/P: SOC 2 / ISO 27001 vendor evidence, SSO+MFA, role-based access, tested restore.
Initial investment < RM 1.5m (fully loaded, Base) | PASS | PASS | FAIL | PASS | Loaded base: A 0.27m; B 1.19m; P 1.32m; C 1.93m (vendor 1.32m + 19.5% overrun + backfill + hardware + cyber).
Downside budget headroom (40% overrun) | PASS | PASS | FAIL | CONDITIONAL | Downside loaded: A 0.30m; B 1.40m; P 1.54m (breaches by RM 0.04m - cap on commitment); C 2.36m.
Implementation within 12 months | PASS | CONDITIONAL | FAIL | CONDITIONAL | B go-live ~month 11 incl. selection; P month 12; C month 14.
Management capacity (3 IT staff) | PASS | CONDITIONAL | FAIL | CONDITIONAL | Requires named business process owners, ERP partner PMO, backfill for key users, 1 ERP admin hire/contractor.

## TCO
Five-year total cost of ownership (Base case, RM)
Values from the Five-Year Financial Model (Base). TCO excludes benefits.
Component | A | B | C | P
Vendor/implementation estimate | 220000 | 820000 | 1320000 | 910000
Overrun allowance (Base) | 19800 | 123000 | 257400 | 136500
Internal backfill, cyber set-up, hardware | 30000 | 250000 | 350000 | 270000
Recurring: licences & support (5 yrs, inflated) | 285576 | 1125383 | 1929227 | 1107883
Recurring: ERP admin, cyber & governance (5 yrs) | 70000 | 441667 | 770833 | 433333
Five-year TCO | 625376 | 2760050 | 4627460 | 2857716
Initial investment (loaded) | 269800 | 1193000 | 1927400 | 1316500
Headroom to RM 1.5m cap | 1230200 | 307000 | -427400 | 183500
5-yr TCO as % of 2026 revenue (RM 48.6m) | 1.287% | 5.679% | 9.522% | 5.88%

## Vendor_Criteria
Vendor evaluation criteria and RFP scorecard
Score each shortlisted vendor 1-5; weights are editable.
Category | Criterion | Weight | Vendor 1 | Vendor 2 | Vendor 3 | Pass/fail gate?
Functional fit | Multi-plant inventory, bin/lot control, MRP-lite, shop-floor reporting | 15% |  |  |  | Y
Functional fit | Lot traceability and revision control (automotive / semiconductor customers) | 8% |  |  |  | Y
Functional fit | Malaysian statutory: SST, e-invoicing (MyInvois), multi-currency SGD/THB/VND - confirm current phase | 8% |  |  |  | Y
Security | Vendor assurance (ISO 27001 / SOC 2), SSO + MFA, role-based access, audit trail, encryption | 10% |  |  |  | Y
Security | Backup/DR: RPO <= 4h, RTO <= 8h, data residency, exit/data-return clause | 6% |  |  |  | Y
Commercial | Fixed-price implementation with milestone payments and 15% holdback | 8% |  |  |  | N
Commercial | Licence cap: price increase <= 3% p.a. for 3 years; user-tier flexibility | 8% |  |  |  | N
Delivery | Partner references in Malaysian SME manufacturing (>= 3), local support hours | 8% |  |  |  | N
Delivery | Data migration tooling and cleansing support | 7% |  |  |  | N
Delivery | Implementation plan with plant-by-plant cutover and rollback | 6% |  |  |  | N
Scalability | Open APIs; add-on BI / planning module available later without re-platforming | 6% |  |  |  | N
Usability | Mobile/scanner support, role-based screens, training content | 5% |  |  |  | N
Integration | Connector to existing accounting software or finance module migration path | 5% |  |  |  | N
| Weighted score | 100% | 0 | 0 | 0