SAFFRON ROUTE FOODS PVT. LTD. | MALAYSIA MARKET ENTRY

Entry Strategy Evaluation

Four ways into Malaysia compared, and the recommended path

# 1. Recommendation

Enter Malaysia through a partner-led hybrid: a licensed local distributor for modern trade and ethnic grocers, plus a Saffron Route-controlled digital layer (Shopee, TikTok Shop, Lazada, own D2C) and a small foodservice team. Commit capital in stages, with the option to step up to local co-packing or a joint venture once the market is proven.

Base case: NPV MYR 11.8m (MYR 7.4m on an exit-multiple cross-check), operating break-even in Year 3, Year-5 revenue MYR 30.0m (about INR 62 crore) at a 13% EBIT margin, and a peak funding need of MYR 8.3m (about INR 17 crore).

# 2. The four alternatives

| Option | How it works | Strengths | Weaknesses |
| --- | --- | --- | --- |
| Direct entry | Own Malaysian subsidiary, sales force, warehouse and trade marketing | Full control, highest margin per unit (46% gross), brand ownership | Highest fixed cost and capital (MYR 3m up front), slow listings, foreign-ownership licensing questions |
| Local distribution partnership | Licensed importer-distributor holds stock and sells to trade | Fast, low capital, halal and listing know-how, immediate door reach | Lower margin (36% gross), less brand and data control, partner dependence |
| Joint venture (51:49) | Shared entity with a Malaysian food company, potentially with local co-packing | Local credibility, shared capital, option to make locally and lower COGS | Slow to set up, governance risk, Saffron funds 51% of capex |
| Digital-first | Marketplaces and D2C with 3PL fulfilment | Cheapest test, highest margin, direct consumer data | Online is a small share of packaged-food sales, CAC-heavy, cannot reach scale alone |

# 3. Financial comparison

All four modes are run on the same SOM path with mode-specific margins, fixed costs, ramp speed and capital (Mode_Compare sheet). The hybrid is valued in the full five-year model, so read the ranking as directional.

| Option | NPV (MYR m) | Peak funding (MYR m) | Year-5 revenue (MYR m) | Year-5 EBITDA margin | Score (of 5) |
| --- | --- | --- | --- | --- | --- |
| Direct entry (own subsidiary) | -20.0 | 24.7 | 30.1 | 4% | 2.10 |
| Local distribution partnership | 0.9 | 6.6 | 28.6 | 10% | 3.64 |
| Joint venture (51:49) | -9.3 | 10.9 | 31.6 | 8% | 2.95 |
| Digital-first (marketplace + D2C) | -6.3 | 8.1 | 15.0 | -1% | 3.27 |
| Recommended: partner-led hybrid + digital layer | 11.8 | 8.3 | 30.0 | 13% | 4.55 |

Scores weight financial return 30%, speed 15%, capital at risk 15%, control 15%, halal/local know-how 15%, optionality 10%. The financial score is computed from NPV; other scores are judgements and can be changed in the Entry_Scorecard sheet.

Why the hybrid wins. The distributor delivers door reach and halal/regulatory know-how quickly. The digital layer adds the highest-margin revenue (55% gross margin on online sales versus 38% on retail) and consumer data, and foodservice adds volume. Direct entry and a joint venture carry fixed costs that a MYR 30m business cannot absorb. Digital alone is too small.

# 4. Five-year financials of the recommended path

| MYR m | Y0 2027 | Y1 | Y2 | Y3 | Y4 | Y5 |
| --- | --- | --- | --- | --- | --- | --- |
| Revenue | 0.0 | 2.2 | 7.5 | 14.9 | 22.8 | 30.0 |
| of which retail | 0.0 | 1.1 | 4.5 | 9.5 | 15.0 | 20.0 |
| of which online | 0.0 | 0.8 | 2.1 | 3.7 | 5.3 | 6.9 |
| of which foodservice | 0.0 | 0.3 | 0.9 | 1.7 | 2.5 | 3.2 |
| Gross profit | 0.0 | 1.0 | 3.1 | 6.1 | 9.4 | 12.3 |
| EBITDA | -1.2 | -1.6 | -1.0 | 0.4 | 2.4 | 4.4 |
| EBIT | -1.2 | -1.8 | -1.3 | 0.0 | 1.9 | 3.8 |
| Free cash flow | -2.0 | -2.4 | -2.6 | -1.3 | 0.7 | 2.6 |
| Cumulative FCF | -2.0 | -4.4 | -7.1 | -8.3 | -7.6 | -5.0 |

## 4.1 Scenarios

|  | Bear | Base | Bull | Probability-weighted |
| --- | --- | --- | --- | --- |
| NPV incl. terminal value (MYR m) | -12.1 | 11.8 | 26.3 | 9.4 |
| NPV, exit-multiple cross-check | -12.1 | 7.4 | 20.5 | 5.8 |
| Year-5 revenue (MYR m) | 17.8 | 30.0 | 38.5 | - |
| Year-5 EBIT margin | -6% | 13% | 19% | - |
| Peak funding need (MYR m) | 15.7 | 8.3 | 6.3 | - |
| IRR incl. terminal value | n/m | 44% | 70% | - |

Weights: Bear 25%, Base 50%, Bull 25%. Bear case: door roll-out 35% slower, sales per door 20% lower, COGS +8%, CAC +25%, Year-1 halal/listing delay. The Bear NPV assumes exit after Year 5 with zero terminal value; stage gates would cut losses earlier.

## 4.2 Reading the numbers honestly

- Value sits beyond Year 5. The explicit five-year NPV is MYR -5.2m and cash payback falls after Year 5, so terminal value is 145% of base NPV. The exit-multiple cross-check (5x EBITDA, deliberately conservative) still gives MYR 7.4m. IRR figures (44% and 35%) are high because the investment is small relative to Year-5 value, and should not be quoted without that context.

- Break-even: operating break-even in Year 3. In Year 5, break-even revenue is about MYR 13.8m against MYR 30.0m of revenue, a margin of safety of 54%.

- Online unit economics: LTV/CAC is about 3.8x by Year 3 (CAC MYR 28, lifetime value MYR 108), supporting online as an efficient layer if retention holds near 45%.

## 4.3 Sensitivity

The tornado below shows the NPV change when one driver moves at a time (MYR m, base NPV 11.8).

| Driver | Low case | High case | NPV at low | NPV at high |
| --- | --- | --- | --- | --- |
| Discount rate (WACC) | 14% | 10% | 7.5 | 18.7 |
| Sales per door / foodservice volume | -20% | +20% | 5.6 | 15.3 |
| Door roll-out pace | -20% | +20% | 6.5 | 15.0 |
| COGS (FX, duty, freight) | +5% | -5% | 6.9 | 15.1 |
| Fixed costs (team, G&A) | +20% | -20% | 7.2 | 13.7 |
| Terminal growth | 2% | 4% | 9.9 | 14.1 |
| Net working capital % revenue | 18% | 12% | 9.8 | 13.8 |
| Online new-customer volume | -30% | +30% | 10.3 | 13.2 |
| Trade and brand spend | +20% | -20% | 10.9 | 12.7 |
| Customer acquisition cost | +30% | -30% | 11.1 | 12.5 |

NPV is most exposed to the discount rate, door roll-out pace, sales per door and COGS. Distribution execution, not market growth, decides the outcome, so Phase 1 is designed to prove roll-out pace and throughput per door early.

# 5. Stage-gated roadmap

| Phase | Timing | Scope | Exit gate to proceed |
| --- | --- | --- | --- |
| 0. Validate | Now to Month 6 | Shelf audit, consumer survey, halal certification via a JAKIM-recognised Indian body, product registration, distributor shortlist and term sheet | Halal certificate in hand; distributor signed; price index and spend assumptions confirmed; cap spend near MYR 1.2m |
| 1. Launch | Year 1 | Klang Valley and Johor, about 450 doors, 8-10 SKUs, marketplace and TikTok Shop store, small foodservice pilot | At least 300 doors by Month 9; monthly sales per door at least MYR 400; CAC at or below MYR 35. Cumulative exposure to this point about MYR 4.4m |
| 2. Scale | Years 2-3 | About 2,100 doors, Penang and Negeri Sembilan, frozen range in cold chain, foodservice accounts | Doors at least 1,200 by Month 24; EBIT near break-even by Year 3 |
| 3. Optimise | Years 4-5 | Evaluate local co-packing or a JV to cut COGS and duty exposure; consider a subsidiary when volume justifies fixed cost | EBIT margin above 10% and gross margin above 40% |

# 6. Key risks and mitigations

| Risk | Why it matters | Mitigation |
| --- | --- | --- |
| Halal or registration delay | No halal logo means no mainstream access | Start certification in Month 0; use an Indian body on JAKIM's recognised list; Year-1 delay is in the Bear case |
| Distributor under-performance | Door roll-out and throughput are top NPV drivers | Performance-linked terms, 18-month exclusivity limited by volume, quarterly business reviews |
| FX and duty | INR-MYR moves and tariffs hit landed COGS | Annual price indexing, HS-code duty review, local co-packing option |
| Price pressure from local brands | Value-conscious shoppers and strong incumbents | Hold price index at 115-125 and compete on authenticity and range; avoid deep promotions |
| Online CAC inflation | Social commerce costs can rise quickly | Cap CAC at MYR 35; shift to retention and bundles; LTV/CAC floor of 3x |

# 7. Next steps (first 90 days)

- Appoint a regulatory consultant and file for halal certification through a JAKIM-recognised Indian body.

- Commission the shelf audit and a 600-person consumer survey to replace the low-confidence inputs.

- Issue an RFP to three licensed distributors and negotiate performance-linked terms.

- Open marketplace seller accounts and run a small paid pilot to test CAC and repeat rate before the Year-1 commitment.